## Project Plan
ServiceNow GRC Implementation
Phase | Task | Estimated Effort (Hours) | Resources Needed | Tools | Dependencies
Planning and Initiation | Define project scope and objectives | 4 | Project Manager, GRC SME | MS Teams, Word | Stakeholder availability
Planning and Initiation | Assemble project team | 4 | Project Manager | MS Teams, Email | NA
Planning and Initiation | Conduct stakeholder alignment workshops | 6 | Project Manager, Business Analyst | MS Teams, Miro | Stakeholder calendars
Requirement Gathering and Design | Conduct requirement workshops | 12 | Business Analyst, Process Owners | MS Teams, Excel | Stakeholder availability
Requirement Gathering and Design | Map compliance frameworks | 8 | GRC SME | ServiceNow, Excel | Access to compliance frameworks
Requirement Gathering and Design | Document integration requirements | 6 | Integration Specialist | Excel, Word | Workshop outputs
Configuration and Development | Configure Policy Management | 24 | ServiceNow Developer | ServiceNow | Finalized process design
Configuration and Development | Configure Risk Management | 32 | ServiceNow Developer | ServiceNow | Finalized workflows
Configuration and Development | Integrate vulnerability scanners | 16 | Integration Specialist | APIs, ServiceNow | Scanner APIs, IT approvals
Testing and Validation | Develop test cases | 8 | QA Team, Business Analyst | Excel | Completed configuration
Testing and Validation | Execute unit tests | 16 | QA Team | ServiceNow | Test data available
Testing and Validation | Conduct UAT | 16 | Stakeholders, QA Team | ServiceNow | Stakeholder availability
Training and User Adoption | Develop training materials | 16 | Training Specialist, GRC SME | PowerPoint, Word | Approved workflows and processes
Training and User Adoption | Conduct training sessions | 12 | Training Specialist | MS Teams, ServiceNow | Stakeholder availability
Deployment and Go-Live | Go-live preparations | 4 | Project Manager | ServiceNow | Go-live readiness confirmed
Deployment and Go-Live | Deployment & sanity checks | 8 | ServiceNow Developer | ServiceNow | Production data availability
Post-Implementation Support | Monitor system performance | 2 | Support Team | ServiceNow dashboards | ServiceNow instance monitoring setup

## Sheet1
Task Name | Start Date | Duration (Days) | End Date | Start Days | Adjusted Length
Define scope & objectives | 2025-01-29 | 2 | 2025-01-31 | 0 | 2
Assemble project team | 2025-01-31 | 1 | 2025-02-03 | 2 | 3
Stakeholder alignment workshops | 2025-02-01 | 3 | 2025-02-05 | 3 | 4
Set up ServiceNow dev instance | 2025-02-05 | 2 | 2025-02-07 | 7 | 2
Develop communication plan | 2025-02-07 | 1 | 2025-02-10 | 9 | 3
Requirement workshops | 2025-02-08 | 4 | 2025-02-13 | 10 | 5
Map compliance frameworks | 2025-02-12 | 2 | 2025-02-14 | 14 | 2
Define processes | 2025-02-14 | 4 | 2025-02-20 | 16 | 6
Document integration requirements | 2025-02-20 | 2 | 2025-02-24 | 22 | 4
Configure Policy Management | 2025-02-24 | 5 | 2025-03-03 | 26 | 7
Configure Risk Management | 2025-03-01 | 6 | 2025-03-10 | 31 | 9
Integrate vulnerability scanners | 2025-03-06 | 4 | 2025-03-12 | 36 | 6
Initial data migration | 2025-03-10 | 3 | 2025-03-13 | 40 | 3
Unit testing | 2025-03-15 | 5 | 2025-03-21 | 45 | 6
End-to-end testing | 2025-03-20 | 4 | 2025-03-26 | 50 | 6
Develop training materials | 2025-03-25 | 3 | 2025-03-28 | 55 | 3
Conduct training sessions | 2025-03-28 | 3 | 2025-04-02 | 58 | 5
Go-live preparations | 2025-04-02 | 2 | 2025-04-04 | 63 | 2
Deployment & sanity checks | 2025-04-04 | 2 | 2025-04-08 | 65 | 4
Post-deployment monitoring | 2025-04-06 | 5 | 2025-04-11 | 67 | 5
Formulas:
End Date = WORKDAY([Start Date],[Duration (Days)])